## Timeline
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• The "Tasks" table assumes a Monday-Friday work week
• The "Milestones" table dates are updated based on the "Tasks" table
• Only edit the highlighted input cells; others are formula-based
Tasks
Start | End | Duration (Weeks) | Duration (Business Days) | Task | Status | Vert. Position | Vert. Line
2021-09-13 | 2021-10-01 | 3 | 15 | Send RFI Requests | Complete | -15 | -15 | Input Cells
2021-10-04 | 2021-10-15 | 2 | 10 | Receive RFI Responses | In Progress | -25 | -25 | Formatting Cells (Do not recommende changing)
2021-10-18 | 2021-11-05 | 3 | 15 | Evaluate RFIs | Not Started | -35 | -35
2021-11-08 | 2021-11-12 | 1 | 5 | Send RFPs | Not Started | -45 | -45
2021-11-15 | 2021-12-10 | 4 | 20 | Receive RFPs | Not Started | -55 | -55
2021-12-13 | 2021-12-24 | 2 | 10 | Q&A | Not Started | -65 | -65
2021-12-27 | 2022-01-21 | 4 | 20 | Evaluate RFPs | Not Started | -75 | -75
2022-01-24 | 2022-01-28 | 1 | 5 | Schedule Finals Presentations | Not Started | -85 | -85
2022-01-31 | 2022-02-11 | 2 | 10 | Select Winning Firm | Not Started | -95 | -95
Insert new rows above this one
Milestones
Date | Milestone | Status | Position
2021-09-13 | Send RFI Requests | In Progress | 15
2021-11-08 | Send RFPs | Not Started | 15
2021-12-27 | Selection Process | Not Started | 15
2022-02-11 | Acceptance Letter | Not Started | 15
Insert new rows above this one
Formulas:
End = WORKDAY([Start],([Duration (Business Days)]-1))
Start = WORKDAY([End, row above],1)

## About
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
About FEG
FEG is an independent, full-service investment advisory firm providing investment consulting, outsourced chief investment officer (OCIO), and research services to predominantly nonprofit and institutional clients.
Established in 1988, FEG has approximately $72 billion1 in client assets under advisement, and is headquartered in Cincinnati, Ohio with offices in Dallas, Texas and Indianapolis, Indiana.
1FEG Investment Advisors (also known as Fund Evaluation Group, LLC) is a federally registered investment adviser under the Investment Advisers Act of 1940, as amended, providing non-discretionary and discretionary investment advice to its clients on an individual basis. Registration as an investment adviser does not imply a certain level of skill or training. The oral and written communications of an adviser provide you with information about which you determine to hire or retain an adviser. Fund Evaluation Group, LLC, Form ADV Part 2A & 2B can be obtained by written request directed to: Fund Evaluation Group, LLC, 201 East Fifth Street, Suite 1600, Cincinnati, OH 45202 Attention: Compliance Department. Neither the information nor any opinion expressed on this website constitutes an offer, or an invitation to make an offer, to buy or sell any securities. As of June 30, 2022. Assets under Advisement (AUA) include discretionary and non-discretionary assets of FEG and its affiliated entities. These assets are typically non-discretionary. Some asset values may not be readily available at the most recent quarter-end; therefore, the previous quarter's values were used and may be higher or lower depending on current market conditions. Of the $71.7bn in assets under advisement, FEG's total assets under management (AUM) of $11.3bn includes discretionary ($9.5bn) and non-discretionary AUM ($1.8bn). The assets do not include approximately $7 million in discretionary AUM, with 40 individual clients. Although FEG has an advisory relationship with these clients, they are all maintained via a single third-party relationship with a financial intermediary. Inclusion of these clients would materially change the total number of clients shown above. FEG predominately focuses on servicing institutional clients.